## Production Backlog
October 2017 Production Backlog
Production Name: |  | Down to Earth (DTE) |  |  |  |  | Task List
Primary Maintainer: |  | Charlie Shin |  |  |  |  | Sprint #1
Secondary Maintainer: |  | Bobby Kemp |  |  |  |  | Priority | Feature ID | Status | Task | Output | Notes | Project Priority
Member List | [6 empty] | BE Division
Last Name | First Name | Initials | BE? | FE? | QA? | TL? | 1 | DTE-BE-100 | X | Player Movement | Basic Player movement | 1 | 3
Brewster | Joseph | JB | ü | ü |  |  | 2 | DTE-BE-200 | X | Player Animation | Player animates in game |  | 4
Calderone | Salvatore | SC | ü |  | ü |  | BE Division Note
Gibbs | Joshua | JG | ü | ü |  |  | No. | Note
Gruber | Julia | JR |  | ü |  |  | 1 | Be sure variables is adjustable in editor level
Hietbrink | Noah | NH |  | ü | ü |  | FE Division
Kemp | Bobby | BK | ü |  |  | ü | 1 | DTE-FE-100 | X | Level Mechanic | Create basic level for prototype testing field |  | 1
Morris | Connor | CM | ü |  | ü |  | 2 | DTE-FE-200 | X | Prop Design | Create prefab based props | 1 | 5
Nashed | Rebecca | RN |  | ü |  |  | 3 | DTE-FE-300 | X | UI | Create gauge | 2 | 6
Shin | Charlie | CS | ü | ü | ü | ü | FE Division Note
Division Summary | [6 empty] | No. | Note
Workload Distribution (2017 Oct.) | [6 empty] | 1 | Props must be able to utilize prefab based props
Division | Initial | Focuses On | Programming | Editor | Testing | Total | 2 | Create separate scripts for this
Back-End | BE | Core Mechanic | 70% | 15% | 15% | 100% | QA Division
Front-End | FE | Level, UI | 20% | 60% | 20% | 100% | 1 | DTE-QA-100 | X | Console | Create basic debugging console for displaying data |  | 2
Quality Assurance | QA | Debugging | 30% | 30% | 40% | 100% | 2 | DTE-QA-200 | X | Testing | Test player motion | 1 | 7
[7 empty] | 3 | DTE-QA-300 | X | Testing | Test player interaction with props | 2 | 8
Production Backlog Burn Table | [6 empty] | QA Division Note
Total |  |  | 31 | 31 | 0 | 31 | No. | Note
Sprint 1 | [6 empty] | 1 | If any bug is found, fix it at QA level. If bug is not fixable at QA level, send back to BE and mark as unfinished
Date Start: | 2017 OCT 06 (Friday) |  | Sprint 1 Targets/To Go |  | Sprint 1 Completed/To Go |  | 2 | If any bug is found, fix it at QA level. If bug is not fixable at QA level, send back to FE and mark as unfinished
Date End: | 2017 OCT 12 (Thursday) |  | 8 | 23 | 0 | 31 | Sprint #2
Sprint 2 | [6 empty] | Priority | Feature ID | Status | Task | Output | Notes | Project Priority
Date Start: | 2017 OCT 13 (Friday) |  | Sprint 2 Targets/To Go |  | Sprint 2 Completed/To Go |  | BE Division
Date End: | 2017 OCT 19 (Thrusday) |  | 7 | 16 | 0 | 31 | 1 | DTE-BE-300 | X | Player Status | Basic player status, such as hp, exp, etc. | 1 | 3
Sprint 3 | [6 empty] | 2 | DTE-BE-400 | X | Player Mechanic | Ranged attack (Projectile version) | 1 | 1
Date Start: | 2017 OCT 20 (Friday) |  | Sprint 3 Targets/To Go |  | Sprint 3 Completed/To Go |  | BE Division Note
Date End: | 2017 OCT 26 (Thrusday) |  | 4 | 12 | 0 | 31 | No. | Note
Sprint 4 | [6 empty] | 1 | Create separate scripts for this
Date Start: | 2017 OCT 27 (Friday) |  | Sprint 4 Targets/To Go |  | Sprint 4 Completed/To Go |  | FE Division
Date End: | 2017 NOV 02 (Thrusday) |  | 12 | 0 | 0 | 31 | 1 | DTE-FE-400 | X | Prop Design | Moving platforms | 1 | 2
Overall Production Summary | [6 empty] | 2 | DTE-FE-500 | X | Level Mechanic | Player interaction with NPC | 2 | 4
By the end of 2017, Programming team should have basic prototype, which has capability to show major gameplay | [6 empty] | FE Division Note
mechanics. | [6 empty] | No. | Note
[7 empty] | 1 | Props must be able to utilize prefab based props
[7 empty] | 2 | Create separate scripts for this
QA Division
[7 empty] | 1 | DTE-QA-400 | X | Testing | Test ranged attack mechanism | 1 | 5
[7 empty] | 2 | DTE-QA-500 | X | Testing | Test moving platforms | 2 | 6
[7 empty] | 3 | DTE-QA-600 | X | Testing | Test player interaction with NPC | 2 | 7
QA Division Note
[7 empty] | No. | Note
[7 empty] | 1 | If any bug is found, fix it at QA level. If bug is not fixable at QA level, send back to BE and mark as unfinished
[7 empty] | 2 | If any bug is found, fix it at QA level. If bug is not fixable at QA level, send back to FE and mark as unfinished
Sprint #3
[7 empty] | Priority | Feature ID | Status | Task | Output | Notes | Project Priority
BE Division
[7 empty] | 1 | DTE-BE-500 | X | Player Mechanic | Ranged attack (Raycast version) | 1 | 1
BE Division Note
[7 empty] | No. | Note
[7 empty] | 1 | Create separate scripts for this
FE Division
[7 empty] | 1 | DTE-FE-600 | X | Level Mechanic | Triggered action | 1 | 2
FE Division Note
[7 empty] | No. | Note
[7 empty] | 1 | Props must be able to utilize prefab based props
QA Division
[7 empty] | 1 | DTE-QA-700 | X | Testing | Test ranged attack mechanism | 1 | 3
[7 empty] | 2 | DTE-QA-800 | X | Testing | Test triggered action mechanism | 2 | 4
QA Division Note
[7 empty] | No. | Note
[7 empty] | 1 | If any bug is found, fix it at QA level. If bug is not fixable at QA level, send back to BE and mark as unfinished
[7 empty] | 2 | If any bug is found, fix it at QA level. If bug is not fixable at QA level, send back to FE and mark as unfinished
Sprint #4
[7 empty] | Priority | Feature ID | Status | Task | Output | Notes | Project Priority
BE Division
[7 empty] | 1 | DTE-BE-600 | X | Player Mechanic | Melee attack | 1 | 1
[7 empty] | 2 | DTE-BE-700 | X | Player Mechanic | Player taking damage and death | 1 | 3
[7 empty] | 3 | DTE-BE-800 | X | Player Animation | Damage motion and death motion |  | 4
BE Division Note
[7 empty] | No. | Note
[7 empty] | 1 | Create separate scripts for this
FE Division
[7 empty] | 1 | DTE-FE-700 | X | UI | Quick access menu (pop-up menu) | 2 | 5
[7 empty] | 2 | DTE-FE-800 | X | Level Mechanic | Timed action | 1 | 2
FE Division Note
[7 empty] | No. | Note
[7 empty] | 1 | Props must be able to utilize prefab based props
[7 empty] | 2 | Create separate scripts for this
QA Division
[7 empty] | 1 | DTE-QA-900 | X | Testing | Test melee attack mechanic | 1 | 6
[7 empty] | 2 | DTE-QA-110 | X | Testing | Test player damage and death | 1 | 7
[7 empty] | 3 | DTE-QA-120 | X | Testing | Test player motion | 1 | 8
[7 empty] | 4 | DTE-QA-130 | X | Testing | Test quick access menu | 2 | 9
[7 empty] | 5 | DTE-QA-140 | X | Testing | Test timed action props | 2 | 10
[7 empty] | 6 | DTE-QA-150 | X | Integration | Sort and integrate player mechanisms |  | 11
[7 empty] | 7 | DTE-QA-160 | X | Integration | Sort and integrate level mechanisms |  | 12
QA Division Note
[7 empty] | No. | Note
[7 empty] | 1 | If any bug is found, fix it at QA level. If bug is not fixable at QA level, send back to BE and mark as unfinished
[7 empty] | 2 | If any bug is found, fix it at QA level. If bug is not fixable at QA level, send back to FE and mark as unfinished

## Sprint #1 Chart
Sprint #1 Backlog
General Info |  | Member Info |  |  |  | Task Board
Sprint No.: | 1 | Last Name | First Name | Initials |  | Task ID | Feature ID | Category | Type | Assigned To | On Day | NST | INW | TST | MRG | CMP | Descriptions
Date Start: | 2017OCT06 | Brenster | Joseph | JB |  | DTE-FE-001 | DTE-FE-100 | FE | ED | RN | 4 | O |  |  |  |  | Create prototype; ground with collision box
Date End: | 2017OCT12 | Calderone | Salvatore | SC |  | DTE-FE-002 | DTE-FE-100 | FE | ED | BK | 2 | O |  |  |  |  | Create prototype; platform with collision box
Demo On: | 2017OCT13 | Gibbs | Joshua | JG |  | DTE-FE-003 | DTE-FE-100 | FE | ED | RN | 4 | O |  |  |  |  | Create prototype; add out-of-world boundary box
Category Legend |  | Gruber | Julia | JR |  | DTE-FE-004 | DTE-FE-200 | FE | ED | CS | 2 | O | O | O | O | O | Create parent prefab which will act as multipurpose prop
BE: | Back-End | Hietbrink | Noah | NH |  | DTE-FE-005 | DTE-FE-300 | FE | ED | JG | 4 | O |  |  |  |  | Create simple parent guage; must be animated
FE: | Front-End | Kemp | Bobby | BK |  | DTE-FE-006 | DTE-FE-300 | FE | ED | JG | 4 | O |  |  |  |  | Create testable HP gauge; must be inherited from parent gague
QA: | Quality Assurance | Morris | Connor | CM |  | DTE-BE-001 | DTE-BE-100 | BE | PR | SC | 4 | O |  |  |  |  | Write script for moving a character left and right
Status Legend |  | Nashed | Rebecca | RN |  | DTE-BE-002 | DTE-BE-100 | BE | PR | CM | 4 | O |  |  |  |  | Write script for jumping a character (force-based version)
NST: | Not Started | Shin | Charlie | CS |  | DTE-BE-003 | DTE-BE-100 | BE | PR | SC | 4 | O |  |  |  |  | Write script for jumping a character (translate-based version)
INW: | In-Work |  |  |  |  | DTE-BE-004 | DTE-BE-200 | BE | ED | BK | 2 | O |  |  |  |  | Apply test sprites to character in idle
TST: | Testing |  |  |  |  | DTE-BE-005 | DTE-BE-300 | BE | ED | JB | 2 | O |  |  |  |  | Apply test sprites to character moving left and right
MRG: | Merging |  |  |  |  | DTE-BE-006 | DTE-BE-400 | BE | ED | CS | 3 | O |  |  |  |  | Apply test sprites to character in jumping
CMP: | Completed |  |  |  |  | DTE-QA-001 | DTE-QA-100 | QA | PR | CS | 2 | O | O | O | O | O | Create script that can be applied to various game objects for sending data
Type Legend | [5 empty] | DTE-QA-002 | DTE-QA-100 | QA | ED | CS | 5 | O | O | O | O | O | Create GUI that can display data coming from various game objects
PR: | Programming |  |  |  |  | DTE-QA-003 | DTE-QA-200 | QA | TS | CM | 7 | O | X |  | X |  | Test character basic movement (Left/right)
ED: | Editor |  |  |  |  | DTE-QA-004 | DTE-QA-200 | QA | DB | CM | 7 | O |  |  |  |  | Debug character basic movement (Left/right)
DB: | Debugging |  |  |  |  | DTE-QA-005 | DTE-QA-300 | QA | TS | CS | 7 | O | X |  | X |  | Test prototype field interaction with character
TS: | Testing
Date Table
Day # | Date | Target Tasks | Target To Go | Compl. Tasks | Tasks To Go
1 | 2017OCT06 | 0 | 17 | 0 | 17
2 | 2017OCT07 | 5 | 12 | 0 | 17
3 | 2017OCT08 | 1 | 11 | 3 | 14
4 | 2017OCT09 | 7 | 4 | 0 | 14
5 | 2017OCT10 | 1 | 3 | 0 | 14
6 | 2017OCT11 | 0 | 3 | 0 | 14
7 | 2017OCT12 | 3 | 0 | 0 | 14

## Sprint #2 Chart
Sprint #2 Backlog
General Info |  | Member Info |  |  |  | Task Board
Sprint No.: | 1 | Last Name | First Name | Initials |  | Task ID | Feature ID | Category | Type | Assigned To | On Day | NST | INW | TST | MRG | CMP | Descriptions
Date Start: | 2017OCT13 | Brenster | Joseph | JB |  | DTE-BE-001 | DTE-BE-300 | BE | PR | ? | 1 | O |  |  |  |  | Create variable for HP and test functionality
Date End: | 2017OCT19 | Calderone | Salvatore | SC |  | DTE-BE-002 | DTE-BE-300 | BE | PR | ? | 2 | O |  |  |  |  | Create variable for armour and test functionality
Demo On: | 2017OCT20 | Gibbs | Joshua | JG |  | DTE-BE-003 | DTE-BE-400 | BE | ED | ? | 3 | O |  |  |  |  | Create test projectile for long range attack
Category Legend |  | Gruber | Julia | JR |  | DTE-BE-004 | DTE-BE-400 | BE | PR | ? | 4 | O |  |  |  |  | Write script for player to shoot individual projectile
BE: | Back-End | Hietbrink | Noah | NH |  | DTE-FE-005 | DTE-FE-400 | FE | ED | ? | 1 | O |  |  |  |  | Create prefab for any moving platform
FE: | Front-End | Kemp | Bobby | BK |  | DTE-FE-006 | DTE-FE-500 | FE | ED | ? | 2 | O |  |  |  |  | Create prefab for NPCs
QA: | Quality Assurance | Morris | Connor | CM |  | DTE-FE-001 | DTE-FE-500 | FE | PR | ? | 3 | O |  |  |  |  | Write script for basic NPC interaction (Item drop)
Status Legend |  | Nashed | Rebecca | RN |  | DTE-QA-002 | DTE-QA-400 | QA | TS | ? | 1 | O | X |  | X |  | Test ranged attack system (Focus on collision detection)
NST: | Not Started | Shin | Charlie | CS |  | DTE-QA-003 | DTE-QA-400 | QA | DB | ? | 2 | O |  |  |  |  | Debug ranged attack system at QA level
INW: | In-Work |  |  |  |  | DTE-QA-004 | DTE-QA-500 | QA | TS | ? | 3 | O | X |  | X |  | Test moving platform prefab
TST: | Testing |  |  |  |  | DTE-QA-005 | DTE-QA-500 | QA | DB | ? | 4 | O |  |  |  |  | Debug moving platform at QA level
MRG: | Merging |  |  |  |  | DTE-QA-006 | DTE-QA-600 | QA | TS | ? | 5 | O | X |  | X |  | Test basic NPC interaction
CMP: | Completed |  |  |  |  | DTE-QA-001 | DTE-QA-600 | QA | DB | ? | 6 | O |  |  |  |  | Debug basic NPC interaction at QA level
Type Legend
PR: | Programming
ED: | Editor
DB: | Debugging
TS: | Testing
Date Table
Day # | Date | Target Tasks | Target To Go | Compl. Tasks | Tasks To Go
1 | 2017OCT13 | 3 | 10 | 0 | 13
2 | 2017OCT14 | 3 | 7 | 0 | 13
3 | 2017OCT15 | 3 | 4 | 0 | 13
4 | 2017OCT16 | 2 | 2 | 0 | 13
5 | 2017OCT17 | 1 | 1 | 0 | 13
6 | 2017OCT18 | 1 | 0 | 0 | 13
7 | 2017OCT19 | 0 | 0 | 0 | 13

## Sprint Chart Form
Sprint # Backlog
General Info |  | Member Info |  |  |  | Task Board
Sprint No.: | 1 | Last Name | First Name | Initials |  | Task ID | Feature ID | Category | Type | Assigned To | On Day | NST | INW | TST | MRG | CMP | Descriptions
Date Start: |  | Brenster | Joseph | JB |  | DTE-BE-001 |  | BE
Date End: |  | Calderone | Salvatore | SC |  | DTE-BE-002 |  | BE
Demo On: |  | Gibbs | Joshua | JG |  | DTE-BE-003 |  | BE
Category Legend |  | Gruber | Julia | JR |  | DTE-BE-004 |  | BE
BE: | Back-End | Hietbrink | Noah | NH |  | DTE-BE-005 |  | BE
FE: | Front-End | Kemp | Bobby | BK |  | DTE-BE-006 |  | BE
QA: | Quality Assurance | Morris | Connor | CM |  | DTE-FE-001 |  | FE
Status Legend |  | Nashed | Rebecca | RN |  | DTE-FE-002 |  | FE
NST: | Not Started | Shin | Charlie | CS |  | DTE-FE-003 |  | FE
INW: | In-Work |  |  |  |  | DTE-FE-004 |  | FE
TST: | Testing |  |  |  |  | DTE-FE-005 |  | FE
MRG: | Merging |  |  |  |  | DTE-FE-006 |  | FE
CMP: | Completed |  |  |  |  | DTE-QA-001 |  | QA
Type Legend | [5 empty] | DTE-QA-002 |  | QA
PR: | Programming |  |  |  |  | DTE-QA-003 |  | QA
ED: | Editor |  |  |  |  | DTE-QA-004 |  | QA
DB: | Debugging |  |  |  |  | DTE-QA-005 |  | QA
TS: | Testing |  |  |  |  | DTE-QA-006 |  | QA
Date Table
Day # | Date | Target Tasks | Target To Go | Compl. Tasks | Tasks To Go
1 |  | 0 | 0 | 0 | 0
2 |  | 0 | 0 | 0 | 0
3 |  | 0 | 0 | 0 | 0
4 |  | 0 | 0 | 0 | 0
5 |  | 0 | 0 | 0 | 0
6 |  | 0 | 0 | 0 | 0
7 |  | 0 | 0 | 0 | 0