## Production Backlog Form
Production Task Chart
Production Infromation |  |  |  |  | Feature List
Production Name: |  | Down to Earth (DTE) |  |  | Sprint #1
Primary Maintainer: |  | Salvatore Calderone |  |  | Priority | Feature ID | Status | Feature | Notes | Branch
Secondary Maintainer: |  | Bobby Kemp |  |  | 1 | DTE-PRM-001 | NS | Character Class Design | Design class structure for Character class | Master
Team Information |  |  |  |  | 2 | DTE-PRM-002 | NS | NPC Class Design | Design class structure for NPCs (Non-Hostile) | Master
Division: |  | Programming |  |  | 3 | DTE-PRM-003 | NS | Enemy Class Design | Design class structure for Enemies | Master
Team Lead: |  | Charlie Shin |  |  | 4 | DTE-PRM-004 | NS | Player Class Design | Design class structure for Player | Master
Primary Maintainer: |  | Charlie Shin |  |  | 5 | DTE-PRM-005 | NS | Character Class Implement | Create Character Class script | DTE-PRM-005
Secondary Maintainer: |  | Bobby Kemp |  |  | 6 | DTE-PRM-006 | NS | Player Class Implement | Create Basic Player Class script | DTE-PRM-006
Team Members |  |  |  |  | 7 | DTE-PRM-007 | NS | Enemy Class Implement | Create Basic Enemy Class script | DTE-PRM-007
| Last Name | First Name | Initial | Position | 8 | DTE-PRM-008 | NS | NPC Class Implement | Create Basic NPC Class script | DTE-PRM-008
1 | Shin | Charlie | CS | Team Lead | 9
2 | Brenster | Joseph | JB |  | 10
3 | Morris | Connor | CM |  | Sprint #2
4 | Kemp | Bobby | BK |  | Priority | Feature ID | Status | Feature | Notes | Branch
5 | Gibbs | Joshua | JG |  | 1 | DTE-PRM-009 | NS | Player Health | Damage only. No healing | DTE-PRM-0911
6 | Calderone | Salvatore | SC |  | 2 | DTE-PRM-010 | NS | Enemy Health | Damage only. No healing | DTE-PRM-0911
7 |  |  |  |  | 3 | DTE-PRM-011 | NS | NPC Health | Damage only. No healing | DTE-PRM-0911
8 |  |  |  |  | 4 | DTE-PRM-012 | NS | Enemy Attack | Melee Attack to player | DTE-PRM-1213
9 |  |  |  |  | 5
10 |  |  |  |  | 6
Team Production Summary |  |  |  |  | 7
Programming team's plan is to have basic character definitions set up before Thanksgiving week. After Thanksgiving week, UI and Environment will be implemented |  |  |  |  | 8
9
10
Sprint #3
[5 empty] | Priority | Feature ID | Status | Feature | Notes | Branch
Production Backlog Burn Table |  |  |  |  | 1
Total |  | 12 | 0 | 12 | 2
Sprint #1 |  |  |  |  | 3
Date Start | 2017NOV10 | Targets | Completed | To Go | 4
Date End | 2017NOV16 | 8 | 0 | 8 | 5
Sprint #2 |  |  |  |  | 6
Date Start | 2017NOV17 | Targets | Completed | To Go | 7
Date End | 2017NOV23 | 4 | 0 | 4 | 8
Sprint #3 |  |  |  |  | 9
Date Start | 2017NOV24 | Targets | Completed | To Go | 10
Date End | 2017NOV30 | 0 | 0 | 0 | Sprint #4
Sprint #4 |  |  |  |  | Priority | Feature ID | Status | Feature | Notes | Branch
Date Start | 2017DEC01 | Targets | Completed | To Go | 1
Date End | 2017DEC07 | 0 | 0 | 0 | 2
3
4
5
6
7
8
9
10

## Sprint #1 Backlog
Sprint #1 Backlog
Sprint Overview
Sprint Start: | 2017NOV10
Sprint End: | 2017NOV16
Demo On: | 2017 NOV 17
Date Table
Day # | Is On | Target Tasks | Target To Go | Comp. Tasks | Tasks To Go
1 | 2017NOV10 | 7 | 6 | 5 | 8
2 | 2017NOV11 | 1 | 5 | 0 | 8
3 | 2017NOV12 | 1 | 4 | 0 | 8
4 | 2017NOV13 | 1 | 3 | 0 | 8
5 | 2017NOV14 | 1 | 2 | 0 | 8
6 | 2017NOV15 | 1 | 1 | 0 | 8
7 | 2017NOV16 | 1 | 0 | 0 | 8
Remember: Baby Steps!
Task Board
Task ID | Feature ID | Started By | Day Projected | NST | INW | TST/RVW | MRG | CMP | Day Finished | Finished By | Task Description
PRM001 | DTE-PRM-001 | ALL | 1 | O | X | X | X | O | 1 | ALL | Construct Character Class, which will become parent class for others
PRM002 | DTE-PRM-002 | ALL | 1 | O | X | X | X | O | 1 | ALL | Construct NPC Class, inherited from Character class
PRM003 | DTE-PRM-003 | ALL | 1 | O | X | X | X | O | 1 | ALL | Construct Enemy Class, inherited from Character class
PRM004 | DTE-PRM-004 | ALL | 1 | O | X | X | X | O | 1 | ALL | Construct Player class inherited from Character class
PRM005 | N/A | ALL | 1 | O | X | X | X | O | 1 | ALL | Adjust Class Structures
PRM006 | N/A | SC | 1 | O | O | [5 empty] | Design Single Level for feature testing
PRM007 | DTE-PRM-006 |  | 2 | O | [6 empty] | Player Movement Phase I: Left and right with sprite inversion
PRM008 | DTE-PRM-006 |  | 3 | O | [6 empty] | Player Movement Phase II: Single jump
PRM009 | DTE-PRM-006 |  | 4 | O | [6 empty] | Player Movement Phase III: Camera control
PRM010 | DTE-PRM-007 |  | 5 | O | [6 empty] | Enemy Movement Phase I: Enemy approaching to player
PRM011 | DTE-PRM-007 |  | 6 | O | [6 empty] | Enemy Movement Phase II: Enemy pathfinding (As simple as possible)
PRM012 | DTE-PRM-008 |  | 7 | O | [6 empty] | NPC Movement Phase I: NPC following player
PRM013 | N/A |  | 1 | O | [6 empty] | Create Character Super Class Script

## Sprint #2 Backlog
Sprint #2 Backlog
Sprint Overview
Sprint Start: | 2017NOV03
Sprint End: | 2017NOV09
Demo On: | TBD
Date Table
Day # | Is On | Target Tasks | Target To Go | Comp. Tasks | Tasks To Go
1 | 2017NOV03 | 1 | 6 | 2 | 5
2 | 2017NOV04 | 1 | 5 | 0 | 5
3 | 2017NOV05 | 1 | 4 | 0 | 5
4 | 2017NOV06 | 1 | 3 | 0 | 5
5 | 2017NOV07 | 1 | 2 | 0 | 5
6 | 2017NOV08 | 1 | 1 | 0 | 5
7 | 2017NOV09 | 1 | 0 | 0 | 5
Remember: Baby Steps!
Task Board
Task ID | Feature ID | Started By | Day Projected | NST | INW | TST/RVW | MRG | CMP | Day Finished | Finished By | Task Description
ABC-### | DTE-ABC-### | INITIALS | 1 | O | O | O | O | O | 1 | INITIALS | Type detailed task description(Not to long, but enough to understand)
ABC-### |  |  | 2 | O | O | O | O | O | 1
ABC-### |  |  | 3 | O | O | O
ABC-### |  |  | 4 | O | O
ABC-### |  |  | 5 | O
ABC-### |  |  | 6 | O
ABC-### |  |  | 7 | O

## Sprint #3 Backlog
Sprint #3 Backlog
Sprint Overview
Sprint Start: | 2017NOV03
Sprint End: | 2017NOV09
Demo On: | TBD
Date Table
Day # | Is On | Target Tasks | Target To Go | Comp. Tasks | Tasks To Go
1 | 2017NOV03 | 1 | 6 | 2 | 5
2 | 2017NOV04 | 1 | 5 | 0 | 5
3 | 2017NOV05 | 1 | 4 | 0 | 5
4 | 2017NOV06 | 1 | 3 | 0 | 5
5 | 2017NOV07 | 1 | 2 | 0 | 5
6 | 2017NOV08 | 1 | 1 | 0 | 5
7 | 2017NOV09 | 1 | 0 | 0 | 5
Remember: Baby Steps!
Task Board
Task ID | Feature ID | Started By | Day Projected | NST | INW | TST/RVW | MRG | CMP | Day Finished | Finished By | Task Description
ABC-### | DTE-ABC-### | INITIALS | 1 | O | O | O | O | O | 1 | INITIALS | Type detailed task description(Not to long, but enough to understand)
ABC-### |  |  | 2 | O | O | O | O | O | 1
ABC-### |  |  | 3 | O | O | O
ABC-### |  |  | 4 | O | O
ABC-### |  |  | 5 | O
ABC-### |  |  | 6 | O
ABC-### |  |  | 7 | O

## Sprint #4 Backlog
Sprint #4 Backlog
Sprint Overview
Sprint Start: | 2017NOV03
Sprint End: | 2017NOV09
Demo On: | TBD
Date Table
Day # | Is On | Target Tasks | Target To Go | Comp. Tasks | Tasks To Go
1 | 2017NOV03 | 1 | 6 | 2 | 5
2 | 2017NOV04 | 1 | 5 | 0 | 5
3 | 2017NOV05 | 1 | 4 | 0 | 5
4 | 2017NOV06 | 1 | 3 | 0 | 5
5 | 2017NOV07 | 1 | 2 | 0 | 5
6 | 2017NOV08 | 1 | 1 | 0 | 5
7 | 2017NOV09 | 1 | 0 | 0 | 5
Remember: Baby Steps!
Task Board
Task ID | Feature ID | Started By | Day Projected | NST | INW | TST/RVW | MRG | CMP | Day Finished | Finished By | Task Description
ABC-### | DTE-ABC-### | INITIALS | 1 | O | O | O | O | O | 1 | INITIALS | Type detailed task description(Not to long, but enough to understand)
ABC-### |  |  | 2 | O | O | O | O | O | 1
ABC-### |  |  | 3 | O | O | O
ABC-### |  |  | 4 | O | O
ABC-### |  |  | 5 | O
ABC-### |  |  | 6 | O
ABC-### |  |  | 7 | O